ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

Municipality of Negotino

## Current situation in the sector

Access to healthcare for the elderly in North Macedonia faces challenges with fragmented systems, increasing demand, and underfunded social care, though reforms are underway, including home visits by nurses, digital health tools (Moe Zdravje app), and projects to improve long-term care (LTC), heavily relying on family/informal care, with government efforts focused on integrating health and social services to meet needs, especially in rural areas.  As the population ages in North Macedonia, the family structures are changing and the health and social systems have limited capacity to provide integrated and person-centred care, leaving older people in the country to face a number of health, social and economic challenges (World Health Organization).

In order to tackle the health and social challenges of the ageing population, over the past few years the Ministry of Labour and Social Policy adopted the National Strategy for Elderly People 2010–2020 and the Action Plan for Healthy Ageing 2020. The Ministry of Health introduced several initiatives to provide greater access to health services for older people, such as home visits by community nurses (also called patronage nurses), the rural doctors project1 and mobile pharmacies, as well as piloting the introduction of integrated health and social services. Furthermore, the Ministry of Health – supported by WHO – initiated a health system reform under which the strengthening of primary health care (PHC) was identified as a key intervention to improve the quality, continuity and overall performance of health services. The reform aims to ensure equitable access to health care and to rebuild a responsive PHC that helps converge health protection and promotion, disease prevention, and primary curative services on the one hand with highly needed public health population-based and social interventions on the other hand. North Macedonia has an established model of integrated palliative and geriatric care at the tertiary level. However, with seven specialist palliative care adult services (0.4 per 100,000 people) and none at all for children, there is insufficient capacity to meet current and projected demand. My role was to understand the national context and work with stakeholders to develop strategies to implement best practice.

# OBJECTIVES & EXPECTED OUTPUTS

The ElderCare project addresses the growing challenge of dementia in the cross-border area of Pella in Greece and Negotino  in North Macedonia. In both regions, the number of elderly people living with dementia is rising, while access to specialised care remains limited—particularly in North Macedonia, where services are fragmented and support systems for families are scarce. ElderCare introduces an innovative, community-based approach designed to improve the quality of life for people with dementia, their caregivers, and elderly individuals at high risk of developing the condition.

Central to the project is the establishment of cross-border, multidisciplinary Memory Teams composed of municipal staff, healthcare professionals and scientific experts. These teams will operate across Pella and the Vardar region, providing personalised care plans, early detection services, and a range of non-pharmaceutical therapies, including occupational, artistic and physical activities, as well as mental training through digital means. Their work will be supported by advanced digital tools, including e-platforms for dementia risk registration, remote support for caregivers and e-learning modules to train both professionals and non-professional volunteers.

The project also brings significant investment in new services and facilities. Mobile health units will deliver care to remote and underserved communities, while in Negotino a Day Center Unit for elderly and vulnerable groups will be established, alongside a specialised rehabilitation centre within the Negotino Public Health Clinic. In Pella, interventions will make use of local facilities and community networks to deliver health services, capacity building for municipal staff and volunteers, and awareness-raising activities to reduce stigma and promote dementia-inclusive communities.

Activities are designed to ensure sustainability by training local staff and volunteers in family- and community-based dementia care, creating a model that can be maintained after the project ends. Scientific support and training will be provided by the Greek Association of Alzheimer’s Disease and Related Disorders and the Institute for Alzheimer’s Disease and Neuroscience, ensuring that all interventions are based on the latest research and best practices.

ElderCare will directly benefit elderly people with dementia, elderly individuals at high risk, caregivers, healthcare professionals, volunteers, and the wider community. It will deliver equal and improved access to dementia care, enhance skills for those providing care, increase social inclusion and create sustainable, community-driven care models that can be replicated elsewhere.

Co-funded by the Interreg VI-A IPA Greece–North Macedonia Programme, the project will be implemented for two years and is expected to reach around 5,000 people per year through improved or new healthcare services, establishing a scalable model for effective cross-border dementia care.

## Overall objective

The overall project objectives are:

- To provide mobile and other health services for elderly people in the cross-border municipalities (including mountainous and remote areas) through mobile Units for Dementia (Memory Teams);

- To provide e-distance health services with modern technological products on both sides of the border;

- To undertake cross-border initiatives for supporting communities to access the primary health care system, in order to secure social and family care

- To promote health and well-being of elderly persons, with a special focus on identified marginalized communities (people with dementia and their care-givers) ensuring equal access to quality and inclusive mainstream services in healthcare;

- To implement interventions non pharmaceutical treatment for the elderly;

- To safeguard the sustainability of the interventions by training the staff of the local entities (municipalities and hospital) and by developing e-training platforms for future members of the “Memory Teams”.

## Specific objective(s)

The specific objective (Outcome) of this contract is as follows:

- Providing requested services necessary for successful implementation of the project

## Expected outputs to be achieved by the contractor

The service will be paid on the basis of the delivery of the specified output(s). Payments might be totally or partially withheld if the contractual result(s) have not been reached in conformity with the detailed terms of reference. Payment(s) is/are based on the approval of this/these deliverable(s). Partial payment has to be determined according to the partial implementation of the output(s).

The expected outputs of this contract are as follows:

Provided Art Therapy for a period of 12 (twelve) months for 8 (eight) beneficiaries;

Provided Occupational Therapy for a period of 12 (twelve) months for 10 (ten) beneficiaries.

Successfully organized and implemented training events for registration/examination of elderly persons carried out by PB5;

Organized and implemented five-day counselling and awareness sessions for caregivers;

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Continued commitment and cooperation of all project partners (PB2 and PB5) during the implementation period;

- Availability and active participation of elderly persons, caregivers and target groups in the planned activities;

- Availability of trained psychiatrists/psychologists and healthcare professionals for implementation of counselling and awareness activities;

- Timely provision of logistical and administrative support necessary for implementation of the activities;

- Continued interest of stakeholders and local communities in activities related to dementia prevention, elderly healthcare and caregiver support.

## Risks

- Possible health-related or epidemiological restrictions impacting group activities and public gatherings;

- Insufficient awareness or understanding among target groups regarding the importance of family-based and community-based care;

# SCOPE OF THE WORK

## General

### Description of the assignment

The assignment of the present contract is to provide organizational, logistical and implementation support for the activities envisaged within the project “Equal Access to Healthcare for the Elderly Population in the Cross-Border Area: Facing the Challenge of Dementia – ElderCare”, through engagement of two (2) executors responsible for organization and support of Art Therapy and Occupational Therapy activities for elderly beneficiaries, as well as organization of events and trainings for registration/examination of the elderly carried out by PB5.

The services should also include support in the promotion of community-based care and assistance in the establishment and implementation of counselling services for prevention of burn-out and depression among caregivers, delivered by trained psychiatrists/psychologists from PB5 with participation of PB2.

### Geographical area to be covered

Municipality of Negotino

### Target groups

The main target groups addressed by the Action are: Residents (including the elderly population and their care givers along with the population in high risk of dementia), Regional and Local Authorities, Disadvantaged and marginalized individuals and social groups, as defined by the Committee on Economic, Social and Cultural Rights.

## Specific work

4.2.1 Organization of training related to registration and examination of elderly persons

The activity foresees organization and logistical support for trainings related to registration and examination of elderly persons, which will be implemented by PB5 within the framework of the project activities under WP3.

The purpose of the activity is to ensure smooth, safe and efficient implementation of the planned trainings and examination sessions for elderly beneficiaries from the target cross-border area. The activity includes all necessary organizational, administrative and logistical arrangements required for successful realization of the events.

The event organization support shall include:

- preparation and coordination of the training schedule and agenda;

- identification and arrangement of appropriate training/event venues;

- coordination of participants and communication with target groups;

- preparation of attendance lists and supporting documentation;

- technical and logistical support during implementation of the trainings;

- organization of seating arrangements, presentation equipment and supporting materials;

- coordination with trainers, healthcare professionals and project partners;

- support for visibility and information activities related to the trainings;

- ensuring appropriate conditions for participation of elderly persons and vulnerable groups;

- preparation of photo documentation and event records where applicable.

The trainings will focus on registration, examination and healthcare support procedures for elderly persons and will contribute to strengthening healthcare access, early detection and support services for the elderly population within the project area.

The need for this activity arises from the necessity to provide adequate organizational and operational conditions for safe implementation of the trainings, considering the involvement of elderly beneficiaries and healthcare professionals.

As a result of the activity, the beneficiary will obtain:

- one report documenting the organization and implementation of the events/trainings;

- participant lists and supporting attendance documentation;

- evidence of implemented logistical and organizational support activities.

The activity has direct synergies with all deliverables under WP3, as it contributes to the implementation of healthcare-related activities, awareness raising, stakeholder involvement and support services for elderly persons within the project.

4.2.2 External expertise for Occupational therapy

The activity foresees engagement of external expertise for provision of Occupational Therapy services for persons with special needs within the framework of the project activities. The activity is aimed at improving functional abilities, social inclusion, independence and quality of life of the beneficiaries through structured therapeutic support.

The action is considered essential due to the specific needs of vulnerable persons and the importance of individualized therapeutic interventions that support physical, cognitive, emotional and social functioning of the participants.

A total of 8 persons with special needs will receive Occupational Therapy services delivered by qualified occupational therapists or experts with relevant professional background and experience.

The implementation of the activity will include:

- preparation of individual assessment and therapy plans for each beneficiary;

- organization and implementation of occupational therapy sessions;

- monitoring of the progress and participation of beneficiaries;

- coordination with caregivers, family members and project staff;

- preparation of attendance records and implementation documentation;

- reporting on the implemented therapy activities and achieved results.

The activity will be implemented over a period of 12 months in accordance with the project implementation schedule and the needs of the beneficiaries.

The implementation dynamics foresees:

- identification and selection of beneficiaries;

- initial assessment sessions;

- regular therapy sessions conducted according to individual needs and therapy plans;

- continuous monitoring and evaluation of progress.

### Therapy sessions

The Occupational Therapy activities will be organized through individual and/or small group sessions depending on the condition and needs of the beneficiaries.

Indicatively, the implementation may include:

- minimum 2 sessions per week;

- sessions with duration of approximately 60–90 minutes;

- practical exercises for development of motor, cognitive, communication and daily living skills;

- activities supporting independence and social interaction;

- therapeutic exercises adapted to the age and condition of the beneficiaries.

The exact number and schedule of sessions may be adjusted according to the professional assessment of the therapist and the individual needs of the participants.

As a result of the activity:

- 8 persons will receive Occupational Therapy services;

- individual therapeutic support plans will be implemented;

- attendance lists and therapy records will be prepared;

- progress monitoring documentation and implementation reports will be produced.

4.2.3 External expertise for Art therapy

The activity foresees engagement of external expertise for implementation of Art Therapy activities for persons with special needs within the framework of the project activities. The activity aims to provide psychosocial support, encourage emotional expression, improve communication skills and promote social inclusion and well-being of the beneficiaries through creative and therapeutic activities.

The action is considered essential due to the importance of therapeutic and creative approaches in supporting people with special needs, especially in relation to emotional stability, self-confidence, communication and social interaction.

A total of 10 persons with special needs will receive Art Therapy services delivered by qualified experts with relevant professional background and experience in Art Therapy, psychology, special education or related fields.

The implementation of the activity will include:

- preparation of individual and group therapy approaches adapted to the beneficiaries;

- organization and implementation of Art Therapy sessions;

- preparation of materials and creative therapeutic activities;

- monitoring of participation and progress of beneficiaries;

- coordination with caregivers, family members and project staff;

- preparation of attendance records and implementation documentation;

- reporting on implemented activities and achieved results.

The activity will be implemented over 12 months in accordance with the project implementation timeline and the needs of the beneficiaries.

The implementation dynamics foresees:

- identification and inclusion of beneficiaries;

- introductory and assessment sessions;

- regular Art Therapy sessions conducted according to the planned schedule;

- continuous monitoring and adaptation of activities based on beneficiaries’ needs and participation.

The Art Therapy activities will be organized through individual and/or group sessions depending on the needs and abilities of the participants.

Indicatively, the implementation may include:

- minimum 2 sessions per week;

- sessions with duration of approximately 60–90 minutes;

- creative activities including drawing, painting, handcrafts and other therapeutic artistic methods;

- activities aimed at improving emotional expression, concentration, communication and social interaction;

- therapeutic exercises adapted to the age and condition of the beneficiaries.

The exact number and schedule of sessions may be adjusted according to the professional assessment of the therapist and the individual needs of the participants.

As a result of the activity:

- 10 persons will receive Art Therapy services;

- therapeutic and creative support activities will be implemented;

- attendance lists and session records will be prepared;

- implementation reports and progress documentation will be produced.

4.2.4 Promotion of the family-based care

The activity foresees promotion of family-based and community-based care services and establishment of a counselling service for prevention of burn-out and depression among caregivers of elderly persons and vulnerable groups.

The activity will be implemented through engagement of trained psychiatrists/psychologists from PB5 who will act as responsible speakers and counsellors, with participation and support from PB2. The activity aims to strengthen psychosocial support mechanisms for caregivers, improve awareness regarding mental health and caregiver well-being, and promote sustainable family-based care approaches within the target communities.

The need for this activity arises from the increasing emotional and psychological burden experienced by caregivers of elderly persons, especially those caring for people with dementia and chronic health conditions. Continuous caregiving responsibilities often result in stress, burn-out, anxiety and depression, which directly affect both caregivers and the quality of care provided to elderly beneficiaries.

The implementation of the activity will include organization and implementation of counselling and awareness sessions for caregivers;

The activity will be implemented through four (4) months.

The organization costs foreseen under the activity include implementation of a five-day counselling and awareness session.

The sessions may include:

- lectures and presentations by psychiatrists/psychologists;

- group counselling and discussions;

- practical guidance for stress management and burn-out prevention;

- awareness raising on depression prevention and mental health support;

- exchange of experiences and best practices among caregivers;

- promotion of family-based and community-based care models.

The sessions will be organized in an accessible and safe environment suitable for participation of caregivers and vulnerable groups.

As a result of the activity:

- counselling and awareness services for caregivers will be established and implemented;

- caregivers will receive psychosocial support and guidance;

- one report documenting the implemented activities and sessions will be prepared;

- participant lists and supporting documentation will be produced;

- increased awareness regarding prevention of burn-out and depression among caregivers will be achieved.

## Project management

### Responsible body

The Contracting Authority is Municipality of Negotino, Republic of North Macedonia and in that capacity, it is responsible to launch the service tender procedure, sign the service contract, authorize payments to the contractor and handle the financial management and control during project implementation. The day-to-day operational project implementation will be performed by Municipality of Negotino, Project office – which is responsible for implementation of project

### Management structure

The project “Equal access to health care for the elderly population in the cross-border area: facing the challenge of dementia”. is implemented by Municipality of Pella from Greece in partnership with Municipality of Negotino and 3 other partners. Municipality of Negotino will be the Contracting Authority responsible for regular coordination as well as coordination with the other partners and will have the overall responsibility of implementation of the project activities in Republic of North Macedonia

### Facilities to be provided by the contracting authority and/or other parties

The Contracting Authority will provide all available information and will fully co-operate with the Consultant in order to achieve the best results. Technical information and access to the existing records, any useful information and/or documentation which may be relevant to the performance of the Contract will be provided upon request.

# LOGISTICS AND TIMING

## Location

Municipality of Negotino

## Start date & period of implementation of tasks

The intended start date is 10.07.2026 and the period of implementation of the contract will be 14 months from this date.

# REQUIREMENTS

## Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be able to provide input as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well on any potential interference or conflict of interest of the proposed expert in his/her function as expert and his/her present or previous functions working as civil servant. Moreover, proof should be submitted that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts who provide input to the contract must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Experts

Minimum requirements for experts are not defined

### Support facilities & backstopping

The costs for support facilities, including backstopping, are included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert providing input to the contract is to be provided by the contracting authority.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original:

Final report of maximum 3 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

## Submission and approval of reports

The report referred to above must be submitted to the project coordinator. The project coordinator is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Provided Art Therapy for a period of 12 (twelve) months for 8 (eight) beneficiaries;

Provided Occupational Therapy for a period of 12 (twelve) months for 10 (ten) beneficiaries.

Successfully organized and implemented training events for registration/examination of elderly persons carried out by PB5;

Organized and implemented five-day counselling and awareness sessions for caregivers;

## Special requirements

N.A.

* * *